## Risks
Age Connects Morgannwg - Risk Log - Cynon Linc
Risk Ref | Risk Statement | Inherent Impact Score | Inherent Likelihood Score | Inherent Risk Score | Mitigation | Residual Impact score | Residual Likelihood Score | Residual Risk | Last Updated | Last time rag status changed | Risk Owner
| Cynon Linc has to close as the phasing plan is not deliverable, leading to negative media coverage and a loss of reputation | 3 | 3 | 9 | Provide potential contractor with proposed phasing plan at early stage. Discuss phasing plan at first contractor meeting. If risk realised, develop comprehensive communication plan. | 2 | 2 | 4 | 2019-02-04 | 2019-02-04 | Denise
| Practical completion is delayed due to the construction contractor going bust, leading to potential negative pressures on both capital and revenue budgets | 3 | 2 | 6 | Carry out due diligence when inviting contractors to tender. | 3 | 1 | 3 | 2019-02-04 | 2019-02-04 | Denise
| All returned tender prices are significantly over budget as the design requirements have changed from the initial cost estimate, leading to significant value engineering and a building not fit for purpose | 3 | 3 | 9 | Reduce the amount of design change, secure additional budget, carry out value engineering based on priority | 2 | 2 | 4 | 2019-02-04 | 2019-02-04 | Denise
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
Likelihood
| 4 | 4 | 8 | 12 | 16
| 3 | 3 | 6 | 9 | 12
| 2 | 2 | 4 | 6 | 8
| 1 | 1 | 2 | 3 | 4
| Impact | 1 | 2 | 3 | 4

## Score Matrix
Likelihood
| Low | Medium | High | Expected
| Score = 1 | Score = 2 | Score = 3 | Score = 4
| 1-10% chance of risk occurring | 11-50% chance of risk occurring | 51-75% chance of risk occurring | > 75% chance of risk risk occurring
Impact
| Low | Moderate | Material | Severe
Potential Outcomes | Score = 1 | Score = 2 | Score = 3 | Score = 4
Financial | Financial impact of less that 5% | Financial impact of 5-10% | Financial impact of 10-40% | Financial imapct of more than 40%
Legal | legal document has to be resigned | we delay the capital programme as underleases not signed | We have additional costs as our lease agreement did not specify who was responsible for public liability | ACM is closed down due to non compliance with legal agreement
Reputational | Service User/staff member is unhappy | Service User/staff member makes informal complaint | Service User/staff member makes formal complaint | Service User/staff member makes formal complaint to regulatory body/funder
Capital | Users do not like the colour of the walls in the toilets | design for kitchen does not meet all of our needs and reduces some income generating capacity | design for kitchen not fit for purpose and additional work has to be carried out to remedy | First floor structure collapses
Operational | Minor impact to an element of a service | Minor impact on whole service | Significant impact on service | Severe disruption to key services
Operational | Minor negative impact on staff member, volunteer or client | Negative impact on staff member, volunteer or client | Harm to staff member, volunteer or client | Death of staff member, volunteer or client